## Data_Import
id | reference | idProject | idActivityType | name | externalReference | creationDate | idUser | idContact | originType | originId | description | idActivity | idStatus | idResource | handled | handledDate | done | doneDate | idle | idleDate | cancelled | idTargetVersion | result | initialStartDate | validatedStartDate | plannedStartDate | realStartDate | priority | initialEndDate | validatedEndDate | plannedEndDate | realEndDate | idActivityPlanningMode | initialDuration | validatedDuration | plannedDuration | realDuration | wbs | validatedWork | assignedWork | plannedWork | realWork | leftWork | progress | expectedProgress | workElementEstimatedWork | workElementRealWork | workElementLeftWork | workElementCount | validatedCost | assignedCost | plannedCost | realCost | leftCost
|  | 2 | Phase | Start-up Phase |  | 2016-02-13 | rmeske | [5 empty] | recorded | [10 empty] | Mon 6/15/15 | Mon 6/15/15 |  |  | 500 | Fri 6/26/15 | Fri 6/26/15 |  |  | As Soon As Possible | 10 | 10
|  | 2 | Task | Update and deliver Statement of Work |  | 2016-02-13 | rmeske | [5 empty] | recorded | TSD | [9 empty] | Mon 6/15/15 | Mon 6/15/15 |  |  | 500 | Tue 6/16/15 | Tue 6/16/15 |  |  | As Soon As Possible | 2 | 2
|  | 2 | Task | Review Statement of Work |  | 2016-02-13 | rmeske | [5 empty] | recorded | SCE | [9 empty] | Wed 6/17/15 | Wed 6/17/15 |  |  | 500 | Tue 6/23/15 | Tue 6/23/15 |  |  | As Soon As Possible | 5 | 5
|  | 2 | Task | Approve Statement of Work |  | 2016-02-13 | rmeske | [5 empty] | recorded | SCE | [9 empty] | Wed 6/24/15 | Wed 6/24/15 |  |  | 500 | Wed 6/24/15 | Wed 6/24/15 |  |  | As Soon As Possible | 1 day | 1 day
|  | 2 | Task | Internal kickoff meeting |  | 2016-02-13 | rmeske | [5 empty] | recorded | TSD | [9 empty] | Thu 6/25/15 | Thu 6/25/15 |  |  | 500 | Thu 6/25/15 | Thu 6/25/15 |  |  | As Soon As Possible | 1 day | 1 day
|  | 2 | Task | Project kickoff meeting |  | 2016-02-13 | rmeske | [5 empty] | recorded | Team | [9 empty] | Fri 6/26/15 | Fri 6/26/15 |  |  | 500 | Fri 6/26/15 | Fri 6/26/15 |  |  | As Soon As Possible | 1 day | 1 day